## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2025-03-09 | OCR output not extracting full address from Aadhaar image | Sprint 1 | Backend Team | Functional | Improved preprocessing and added Tesseract config for multi-line extraction | 2025-04-09 | Closed | Verified successfully
2 | 2025-07-09 | Model output returning inconsistent address verification scores | Sprint 2 | Backend Team | Algorithmic | Adjusted threshold values and retrained model | 2025-08-09 | Closed | Performance improved
3 | 2025-10-09 | Frontend not displaying fraud prediction results correctly | Sprint 2 | Frontend Team | UI/Integration | Fixed JSON parsing and updated API endpoint in React | 2025-11-09 | Closed | Tested and verified
4 | 13/09/2025 | GNN model showing NaN values during training | Sprint 2 | Backend Team | Model Training | Normalized data and fixed null entries in graph edges | 14/09/2025 | Closed | Stable model output
5 | 18/09/2025 | AML check module failing on duplicate address input | Sprint 3 | Backend Team | Logic | Added address hashing and duplicate detection rule | 19/09/2025 | Closed | Verified via testing
6 | 21/09/2025 | Upload form not handling invalid file formats | Sprint 3 | Frontend Team | UI/Validation | Added MIME type check and error popup | 22/09/2025 | Closed | User-friendly validation added
7 | 25/09/2025 | Real-time pipeline response delay | Sprint 3 | Backend Team | Performance | Implemented async processing and caching | 26/09/2025 | Closed | Latency reduced by 35%
8 | 2025-01-10 | Dashboard graphs not updating after backend changes | Sprint 4 | Frontend Team | Integration | Re-linked data binding with new API route | 2025-02-10 | Closed | Graph sync issue resolved
9 | 2025-03-10 | Fraud alerts not showing in admin view | Sprint 4 | Backend Team | Functional | Fixed alert trigger logic in API | 2025-04-10 | Closed | Verified
10 | 2025-05-10 | Minor typo and alignment issues in UI | Sprint 4 | Frontend Team | UI | Adjusted CSS layout and corrected labels | 2025-06-10 | Closed | Presentation-ready